## Summary
Cleo Diagnostics CSP-01-001 ¦ Monthly trial summary ¦ July 2026
Reporting month July 2026 · Data to 31 Jul 2026 · Citrus export 03 Aug 2026 13:57 UTC · Inventory report 03AUG2026
Sponsor version, draft for review. A person checks every figure before this goes to the sponsor.
Key figures
Area | Measure | July 2026 | To date | Detail
Enrollment | Participants enrolled | 66 | 884
Enrollment | Enrolled per active site | 3.14 | – | 0.71 per active site per week; 21 active sites
Post-surgical | Surgeries complete | 40 | 797
Post-surgical | Pathology reports uploaded | 48 | 687 | 86% of surgeries complete; median 45 days from enrollment
Blood samples | Samples registered | 124 | –
Blood samples | Samples inside registration window | 87.1% | 86.1% | 108 of 124 in Jul 2026
Data queries | Queries raised | 133 | 1004 | 105 closed in Jul 2026
Data queries | Unresolved queries at month end | – | 181 | 129 open, 52 reviewing; median 97 days open
Highlights
• 66 participants enrolled in July 2026, up from 60 in June 2026. Total enrollment is now 884.
• 21 sites are active and enrolled an average of 3.1 participants each in July 2026.
• 678 participants have completed the study, 77% of those enrolled.
• Pathology reports are 86% complete: 687 of 797 participants with surgery have a report uploaded.
• 87% of blood samples registered in July 2026 reached the central lab within the required window.
Needs attention
• Sample shipping: 16 of 124 samples registered in July 2026 arrived outside the required window, and 4 sample pairs were shipped together instead of separately. Sites should ship each sample promptly after collection.
• Missing samples: 40 participants are missing one or both blood samples past the registration deadline.
• Pathology reports: 71 participants are more than 60 days past surgery without a report uploaded.

## Enrollment
Enrollment
Reporting month July 2026 · Data to 31 Jul 2026 · Citrus export 03 Aug 2026 13:57 UTC · Inventory report 03AUG2026
Enrollment activity in July 2026 and cumulative to month end.
Recruitment summary
Counts use the date of each event. Citrus holds no pre-screening date, so pre-screening is not shown.
Measure | July 2026 | To date (to 31 Jul 2026)
Consented | 72 | 974
Enrolled | 66 | 884
Screen failures | 2 | 49
Withdrawals | 2 | 20
Completed study | 44 | 678
Consent to enrollment
Measure | n | Denominator | %
Consented in Jul 2026 and enrolled by month end | 63 | 72 consented in Jul 2026 | 87.5%
Enrolled to date | 884 | 974 consented to date | 90.76%
Screen failures to date | 49 | 974 consented to date | 5.031%
Participant status at month end (31 Jul 2026)
Denominator: 974 participants consented to date.
Status | Participants | % of consented
Consented, not yet enrolled | 41 | 4.209%
Enrolled, active | 186 | 19.1%
Completed | 678 | 69.61%
Withdrawn | 20 | 2.053%
Screen failed | 49 | 5.031%
Total consented | 974 | 100%
Enrollments by site and week, July 2026
Weeks run Monday to Sunday. * Part week: only days inside the month count. Per week = month total ÷ 4.43 weeks. Per month since activation = enrolled to date ÷ months since the site activation date. Activation dates and site types come from the site lookup table.
Site | Type | 29 Jun–5 Jul* | 6 Jul–12 Jul | 13 Jul–19 Jul | 20 Jul–26 Jul | 27 Jul–2 Aug* | Jul 2026 total | Per week | Enrolled to date | Months active | Per month since activation
AP Medical Research | General Onc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 16.46 | 0.12151
Beth Israel Deaconess | Gyn/Onc | 0 | 1 | 1 | 1 | 1 | 4 | 0.90323 | 59 | 9.7577 | 6.0465
Cleveland Clinic | Gyn/Onc | 1 | 2 | 2 | 1 | 3 | 9 | 2.0323 | 63 | 9.6591 | 6.5223
Columbia University Irving Medical Center | Gyn/Onc | 0 | 2 | 0 | 1 | 1 | 4 | 0.90323 | 68 | 9.6591 | 7.04
Duke University Medical Center | Gyn/Onc | 2 | 2 | 1 | 0 | 2 | 7 | 1.5806 | 60 | 10.3819 | 5.7793
ES Clinical Research Group (terminated) | General Gyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | – | –
Eastern Carolina Women's | General Gyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15.54 | 0.06435
Emerald Coast Clinical Research | General Gyn | 0 | 0 | 2 | 0 | 1 | 3 | 0.67742 | 68 | 19.3511 | 3.514
HCA Florida Physicians | Gyn/Onc | 1 | 1 | 1 | 4 | 2 | 9 | 2.0323 | 54 | 5.2895 | 10.2089
Maximos Obgyn | General Gyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 15.0801 | 1.9231
New Horizons Clinical Research | General Gyn | 1 | 0 | 1 | 1 | 2 | 5 | 1.129 | 100 | 23.2608 | 4.2991
Next Innovative Clinical Research | General Gyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 22.3409 | 0.76094
Prime Clinical Research | General Gyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 21.9138 | 0.77577
RUSH University Medical Center | Gyn/Onc | 0 | 2 | 2 | 0 | 0 | 4 | 0.90323 | 44 | 9.4292 | 4.6664
Springfield Clinic | Gyn/Onc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14.6201 | 2.736
The Jackson Clinic | General Gyn | 1 | 1 | 1 | 0 | 0 | 3 | 0.67742 | 43 | 18.7598 | 2.2921
Univ. of Florida Jacksonville | Gyn/Onc | 0 | 2 | 0 | 1 | 3 | 6 | 1.3548 | 39 | 13.5688 | 2.8742
Vast Clinical Research | General Gyn | 1 | 0 | 0 | 0 | 0 | 1 | 0.22581 | 14 | 22.8337 | 0.61313
Velocity Clinical Research | Gyn/Onc | 1 | 1 | 1 | 0 | 2 | 5 | 1.129 | 40 | 14.7844 | 2.7056
Virginia Women's Health Associates | General Gyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 18.1684 | 0.93569
Women's Center of Nevada | Gyn/Onc | 0 | 2 | 0 | 1 | 2 | 5 | 1.129 | 90 | 22.8665 | 3.9359
Women's Health Pavilion | General Gyn | 1 | 0 | 0 | 0 | 0 | 1 | 0.22581 | 18 | 15.3101 | 1.1757
All sites |  | 9 | 16 | 12 | 10 | 19 | 66 | 14.9032 | 884 | – | –
Average per active site (21 sites) |  | 0.42857 | 0.7619 | 0.57143 | 0.47619 | 0.90476 | 3.1429 | 0.70968 | 42.0952 | – | –
Enrollment by site type
Denominator for %: 884 participants enrolled to date. Month rates use active sites only. Enrolled to date includes terminated sites. Site types come from the CLEO-001 site list.
Group | Active sites | Enrolled Jul 2026 | Per site per month | Per site per week | Enrolled to date | % of all enrolled to date
General Gyn | 10 | 13 | 1.3 | 0.29355 | 325 | 36.76%
Gyn/Onc | 10 | 53 | 5.3 | 1.1968 | 557 | 63.01%
General Onc | 1 | 0 | 0 | 0 | 2 | 0.2262%
Academic | 6 | 34 | 5.6667 | 1.2796 | 333 | 37.67%
Non-academic | 15 | 32 | 2.1333 | 0.48172 | 551 | 62.33%
Enrollments by month
Month | Consented | Enrolled | Cumulative enrolled
Sep 2024 | 9 | 6 | 6
Oct 2024 | 8 | 8 | 14
Nov 2024 | 9 | 9 | 23
Dec 2024 | 8 | 5 | 28
Jan 2025 | 20 | 18 | 46
Feb 2025 | 21 | 19 | 65
Mar 2025 | 14 | 12 | 77
Apr 2025 | 25 | 22 | 99
May 2025 | 43 | 38 | 137
Jun 2025 | 38 | 36 | 173
Jul 2025 | 41 | 40 | 213
Aug 2025 | 29 | 29 | 242
Sep 2025 | 42 | 37 | 279
Oct 2025 | 50 | 39 | 318
Nov 2025 | 67 | 64 | 382
Dec 2025 | 46 | 40 | 422
Jan 2026 | 72 | 64 | 486
Feb 2026 | 71 | 62 | 548
Mar 2026 | 98 | 85 | 633
Apr 2026 | 77 | 77 | 710
May 2026 | 53 | 48 | 758
Jun 2026 | 61 | 60 | 818
Jul 2026 | 72 | 66 | 884

## Post-surgical
Post-surgical findings
Reporting month July 2026 · Data to 31 Jul 2026 · Citrus export 03 Aug 2026 13:57 UTC · Inventory report 03AUG2026
Surgeries, pathology report uploads and turnaround for enrolled participants.
Surgery and pathology reports
Surgery complete = a surgery date is entered. Report uploaded = Post-Surgical Findings form complete with a report file.
Measure | July 2026 | To date | Denominator (to date) | % (to date)
Participants enrolled | 66 | 884 |  | –
Surgery complete | 40 | 797 | 884 enrolled | 90.16%
Pathology report uploaded | 48 | 687 | 797 with surgery complete | 86.2%
Awaiting pathology report | – | 110 | 797 with surgery complete | 13.8%
Days from enrollment to pathology report upload
Upload date = 'Completed At' on the Post-Surgical Findings form.
Reports uploaded | Reports | Mean days | Median days | Shortest | Longest
In July 2026 | 48 | 48.038 | 44.9209 | 21.9126 | 91.8303
To date | 687 | 46.2964 | 45.0809 | 17.9107 | 91.8303
Surgery and pathology reports by site
Site | Enrolled | Surgery complete | % of enrolled | Report uploaded | % of surgeries | Awaiting report | Median days to upload | Mean days to upload
AP Medical Research | 2 | 2 | 100% | 2 | 100% | 0 | 51.0551 | 51.0551
Beth Israel Deaconess | 59 | 56 | 94.92% | 48 | 85.71% | 8 | 45.9694 | 46.974
Cleveland Clinic | 63 | 50 | 79.37% | 41 | 82% | 9 | 44.9935 | 45.5355
Columbia University Irving Medical Center | 68 | 65 | 95.59% | 57 | 87.69% | 8 | 45.1086 | 45.2673
Duke University Medical Center | 60 | 50 | 83.33% | 35 | 70% | 15 | 45.941 | 48.0957
ES Clinical Research Group | 1 | 0 | 0% | 0 | – | 0 | – | –
Eastern Carolina Women's | 1 | 1 | 100% | 0 | 0% | 1 | – | –
Emerald Coast Clinical Research | 68 | 65 | 95.59% | 64 | 98.46% | 1 | 47.9643 | 48.1967
HCA Florida Physicians | 54 | 44 | 81.48% | 40 | 90.91% | 4 | 39.4938 | 42.603
Maximos Obgyn | 29 | 29 | 100% | 27 | 93.1% | 2 | 54.8585 | 50.4267
New Horizons Clinical Research | 100 | 92 | 92% | 78 | 84.78% | 14 | 45.561 | 48.045
Next Innovative Clinical Research | 17 | 17 | 100% | 12 | 70.59% | 5 | 37.951 | 43.2001
Prime Clinical Research | 17 | 17 | 100% | 15 | 88.24% | 2 | 47.9361 | 51.3573
RUSH University Medical Center | 44 | 41 | 93.18% | 36 | 87.8% | 5 | 47.0089 | 45.3661
Springfield Clinic | 40 | 37 | 92.5% | 34 | 91.89% | 3 | 42.3532 | 44.5759
The Jackson Clinic | 43 | 39 | 90.7% | 31 | 79.49% | 8 | 44.2103 | 44.1989
Univ. of Florida Jacksonville | 39 | 29 | 74.36% | 27 | 93.1% | 2 | 46.3026 | 48.8426
Vast Clinical Research | 14 | 13 | 92.86% | 13 | 100% | 0 | 46.0007 | 45.6111
Velocity Clinical Research | 40 | 34 | 85% | 28 | 82.35% | 6 | 47.1292 | 45.131
Virginia Women's Health Associates | 17 | 17 | 100% | 15 | 88.24% | 2 | 43.0274 | 45.2189
Women's Center of Nevada | 90 | 82 | 91.11% | 68 | 82.93% | 14 | 41.7866 | 44.6207
Women's Health Pavilion | 18 | 17 | 94.44% | 16 | 94.12% | 1 | 44.9967 | 45.309
All sites | 884 | 797 | 90.16% | 687 | 86.2% | 110 | 45.0809 | 46.2964

## Blood samples
Blood samples
Reporting month July 2026 · Data to 31 Jul 2026 · Citrus export 03 Aug 2026 13:57 UTC · Inventory report 03AUG2026
Central lab registration from the LabConnect inventory report dated 03AUG2026.
Sample registration at the central lab
July 2026 counts samples registered in the month. Each DX1 must be registered within 14 days of collection and each DX2 within 28 days. DX1 and DX2 must ship separately, so a same-day registration is a deviation.
Measure | Jul 2026 n | Jul 2026 denominator | Jul 2026 % | To date n | To date denominator | To date %
Samples registered (DX1 + DX2) | 124 | – | – | 1655 | – | –
DX1 registered within 14 days of collection | 55 | 61 | 90.16% | 759 | 851 | 89.19%
DX2 registered within 28 days of collection | 53 | 63 | 84.13% | 666 | 804 | 82.84%
All samples within their window | 108 | 124 | 87.1% | 1425 | 1655 | 86.1%
Samples outside their window | 16 | 124 | 12.9% | 230 | 1655 | 13.9%
DX1 and DX2 registered on the same day (pairs) | 4 | – | – | 42 | – | –
Sample registration by month
Samples registered at the central lab in each month, last 12 months. Denominator for %: samples registered that month.
Month | Registered | Within window | Outside window | % within window
Aug 2025 | 63 | 54 | 9 | 85.71%
Sep 2025 | 65 | 58 | 7 | 89.23%
Oct 2025 | 75 | 66 | 9 | 88%
Nov 2025 | 106 | 94 | 12 | 88.68%
Dec 2025 | 96 | 80 | 16 | 83.33%
Jan 2026 | 105 | 92 | 13 | 87.62%
Feb 2026 | 106 | 96 | 10 | 90.57%
Mar 2026 | 154 | 129 | 25 | 83.77%
Apr 2026 | 167 | 140 | 27 | 83.83%
May 2026 | 124 | 105 | 19 | 84.68%
Jun 2026 | 98 | 86 | 12 | 87.76%
Jul 2026 | 124 | 108 | 16 | 87.1%
Sample pair status at month end
Denominator: 884 participants enrolled to date. Overdue = the registration window for the missing sample has passed. Pending = still inside the window.
Status | Participants | % of enrolled
Both samples registered | 798 | 90.27%
DX2 missing: pending | 23 | 2.602%
DX2 missing: overdue | 30 | 3.394%
DX1 missing: pending | 0 | 0%
DX1 missing: overdue | 6 | 0.6787%
No sample registered: pending | 19 | 2.149%
No sample registered: overdue | 4 | 0.4525%
No sample: withdrawn, sample not obtained | 4 | 0.4525%
Total enrolled | 884 | 100%
Sample registration by site, to date
Site | Samples registered | DX1 registered | DX1 within 14 days | % DX1 in window | DX2 registered | DX2 within 28 days | % DX2 in window | Same-day pairs | Missing pair: overdue
AP Medical Research | 4 | 2 | 2 | 100% | 2 | 2 | 100% | 0 | 0
Beth Israel Deaconess | 113 | 58 | 49 | 84.48% | 55 | 41 | 74.55% | 1 | 1
Cleveland Clinic | 111 | 57 | 50 | 87.72% | 54 | 47 | 87.04% | 2 | 2
Columbia University Irving Medical Center | 129 | 66 | 57 | 86.36% | 63 | 50 | 79.37% | 2 | 2
Duke University Medical Center | 112 | 58 | 50 | 86.21% | 54 | 44 | 81.48% | 4 | 1
ES Clinical Research Group | 2 | 1 | 1 | 100% | 1 | 1 | 100% | 0 | 0
Eastern Carolina Women's | 2 | 1 | 1 | 100% | 1 | 0 | 0% | 0 | 0
Emerald Coast Clinical Research | 129 | 66 | 57 | 86.36% | 63 | 51 | 80.95% | 2 | 3
HCA Florida Physicians | 97 | 50 | 44 | 88% | 47 | 39 | 82.98% | 4 | 0
Maximos Obgyn | 58 | 29 | 25 | 86.21% | 29 | 25 | 86.21% | 1 | 0
New Horizons Clinical Research | 184 | 95 | 85 | 89.47% | 89 | 74 | 83.15% | 9 | 7
Next Innovative Clinical Research | 33 | 17 | 17 | 100% | 16 | 13 | 81.25% | 0 | 1
Prime Clinical Research | 33 | 17 | 16 | 94.12% | 16 | 14 | 87.5% | 1 | 1
RUSH University Medical Center | 83 | 43 | 40 | 93.02% | 40 | 30 | 75% | 2 | 2
Springfield Clinic | 77 | 40 | 37 | 92.5% | 37 | 32 | 86.49% | 3 | 3
The Jackson Clinic | 83 | 42 | 38 | 90.48% | 41 | 35 | 85.37% | 2 | 2
Univ. of Florida Jacksonville | 67 | 33 | 30 | 90.91% | 34 | 31 | 91.18% | 4 | 2
Vast Clinical Research | 27 | 14 | 13 | 92.86% | 13 | 12 | 92.31% | 0 | 1
Velocity Clinical Research | 73 | 38 | 28 | 73.68% | 35 | 25 | 71.43% | 3 | 2
Virginia Women's Health Associates | 34 | 17 | 16 | 94.12% | 17 | 13 | 76.47% | 1 | 0
Women's Center of Nevada | 169 | 89 | 85 | 95.51% | 80 | 70 | 87.5% | 1 | 5
Women's Health Pavilion | 35 | 18 | 18 | 100% | 17 | 17 | 100% | 0 | 1
All sites | 1655 | 851 | 759 | 89.19% | 804 | 666 | 82.84% | 42 | 36
Where registered samples are now
Status from the inventory report dated 03AUG2026. Denominator: 1655 samples registered to month end.
Current status | Samples | % of registered
In Inventory | 642 | 38.79%
Transferred | 1001 | 60.48%
Destroyed | 12 | 0.7251%

## Data queries
Data queries
Reporting month July 2026 · Data to 31 Jul 2026 · Citrus export 03 Aug 2026 13:57 UTC · Inventory report 03AUG2026
Query status at month end, built from each query's creation and last-update dates.
Query status at month end
Denominator: 1004 queries raised to month end. Reviewing = the site responded and a reviewer is checking it.
Measure | Queries | % of all queries raised
Open | 129 | 12.85%
Reviewing | 52 | 5.179%
Closed | 823 | 81.97%
Total raised to date | 1004 | 100%
Raised in July 2026 | 133 | –
Closed in July 2026 | 105 | –
Open or reviewing for more than 90 days | 93 | –
Days open for unresolved queries
Days open = days from creation to the end of 31 Jul 2026.
Status at month end | Queries | Mean days open | Median days open | Shortest | Longest
Open | 129 | 153.6841 | 89.7268 | 0.039792 | 673.1022
Reviewing | 52 | 168.12 | 128.077 | 0.17963 | 607.165
Open and reviewing | 181 | 157.8314 | 97.2385 | 0.039792 | 673.1022
Queries by site
Percentages use the group's total queries. Days open covers open and reviewing queries.
Site | Total | Open | % open | Reviewing | % reviewing | Closed | % closed | Mean days open | Median days open | Range of days open
AP Medical Research | 1 | 0 | 0% | 0 | 0% | 1 | 100% | – | – | –
Beth Israel Deaconess | 68 | 6 | 8.824% | 1 | 1.471% | 61 | 89.71% | 137.411 | 182.513 | 1–269
Cleveland Clinic | 71 | 8 | 11.27% | 5 | 7.042% | 58 | 81.69% | 88.911 | 71.3289 | 2–237
Columbia University Irving Medical Center | 68 | 6 | 8.824% | 4 | 5.882% | 58 | 85.29% | 141.1536 | 150.9183 | 6–251
Duke University Medical Center | 63 | 13 | 20.63% | 2 | 3.175% | 48 | 76.19% | 54.322 | 12.4633 | 1–230
ES Clinical Research Group | 2 | 0 | 0% | 0 | 0% | 2 | 100% | – | – | –
Eastern Carolina Women's | 1 | 0 | 0% | 0 | 0% | 1 | 100% | – | – | –
Emerald Coast Clinical Research | 70 | 13 | 18.57% | 4 | 5.714% | 53 | 75.71% | 273.8304 | 309.6045 | 1–546
HCA Florida Physicians | 63 | 9 | 14.29% | 6 | 9.524% | 48 | 76.19% | 35.9547 | 10.1631 | 0–128
Maximos Obgyn | 41 | 3 | 7.317% | 1 | 2.439% | 37 | 90.24% | 90.2113 | 38.6862 | 12–271
New Horizons Clinical Research | 117 | 11 | 9.402% | 5 | 4.274% | 101 | 86.32% | 294.1014 | 325.6625 | 9–619
Next Innovative Clinical Research | 18 | 2 | 11.11% | 1 | 5.556% | 15 | 83.33% | 302.1808 | 237.7296 | 157–512
Prime Clinical Research | 19 | 2 | 10.53% | 0 | 0% | 17 | 89.47% | 342.6806 | 342.6806 | 320–365
RUSH University Medical Center | 55 | 10 | 18.18% | 4 | 7.273% | 41 | 74.55% | 88.7033 | 94.5509 | 7–229
Springfield Clinic | 54 | 7 | 12.96% | 6 | 11.11% | 41 | 75.93% | 137.9217 | 78.685 | 0–376
The Jackson Clinic | 53 | 8 | 15.09% | 1 | 1.887% | 44 | 83.02% | 200.9479 | 102.1266 | 0–547
Univ. of Florida Jacksonville | 37 | 2 | 5.405% | 0 | 0% | 35 | 94.59% | 37.0525 | 37.0525 | 3–71
Vast Clinical Research | 23 | 5 | 21.74% | 0 | 0% | 18 | 78.26% | 537.7302 | 627.8354 | 262–673
Velocity Clinical Research | 44 | 10 | 22.73% | 0 | 0% | 34 | 77.27% | 143.7442 | 81.6771 | 5–420
Virginia Women's Health Associates | 24 | 1 | 4.167% | 1 | 4.167% | 22 | 91.67% | 309.4927 | 309.4927 | 202–417
Women's Center of Nevada | 97 | 11 | 11.34% | 10 | 10.31% | 76 | 78.35% | 108.9315 | 41.4594 | 1–436
Women's Health Pavilion | 15 | 2 | 13.33% | 1 | 6.667% | 12 | 80% | 140.1612 | 143.0738 | 124–154
All | 1004 | 129 | 12.85% | 52 | 5.179% | 823 | 81.97% | 157.8314 | 97.2385 | 0–673
Queries by type
Percentages use the group's total queries. Days open covers open and reviewing queries.
Query type | Total | Open | % open | Reviewing | % reviewing | Closed | % closed | Mean days open | Median days open | Range of days open
Missing Data | 773 | 102 | 13.2% | 35 | 4.528% | 636 | 82.28% | 137.9304 | 83.7098 | 0–651
Standard | 231 | 27 | 11.69% | 17 | 7.359% | 187 | 80.95% | 219.7959 | 179.1169 | 1–673
All | 1004 | 129 | 12.85% | 52 | 5.179% | 823 | 81.97% | 157.8314 | 97.2385 | 0–673
Queries by form
Percentages use the group's total queries. Days open covers open and reviewing queries.
Form | Total | Open | % open | Reviewing | % reviewing | Closed | % closed | Mean days open | Median days open | Range of days open
Adverse Events | 64 | 11 | 17.19% | 5 | 7.812% | 48 | 75% | 206.5236 | 172.2152 | 5–598
CA 125 Test, Pre-Surgery | 140 | 13 | 9.286% | 7 | 5% | 120 | 85.71% | 175.6996 | 30.1067 | 10–651
Enrollment | 62 | 6 | 9.677% | 4 | 6.452% | 52 | 83.87% | 158.1139 | 140.3737 | 1–417
Exclusion Criteria | 80 | 13 | 16.25% | 2 | 2.5% | 65 | 81.25% | 119.3345 | 72.0239 | 0–488
Health Information Collection | 145 | 16 | 11.03% | 8 | 5.517% | 121 | 83.45% | 143.0579 | 91.9167 | 0–546
Inclusion Criteria | 75 | 11 | 14.67% | 2 | 2.667% | 62 | 82.67% | 205.5615 | 152.3705 | 1–628
Informed Consent | 74 | 14 | 18.92% | 4 | 5.405% | 56 | 75.68% | 208.439 | 234.9511 | 1–547
Medical History | 65 | 13 | 20% | 3 | 4.615% | 49 | 75.38% | 57.5225 | 15.8222 | 0–212
Post-Surgical Findings | 116 | 19 | 16.38% | 4 | 3.448% | 93 | 80.17% | 139.8362 | 114.1775 | 3–396
Protocol Deviations | 62 | 5 | 8.065% | 2 | 3.226% | 55 | 88.71% | 114.8994 | 21.6708 | 1–619
Study Blood Sample Collection & Processing | 63 | 5 | 7.937% | 10 | 15.87% | 48 | 76.19% | 188.0117 | 103.382 | 11–673
Study Completion | 58 | 3 | 5.172% | 1 | 1.724% | 54 | 93.1% | 189.8267 | 161.0265 | 65–372
All | 1004 | 129 | 12.85% | 52 | 5.179% | 823 | 81.97% | 157.8314 | 97.2385 | 0–673

## Definitions
Definitions and sources
Reporting month July 2026 · Data to 31 Jul 2026 · Citrus export 03 Aug 2026 13:57 UTC · Inventory report 03AUG2026
Reporting month | July 2026. Month counts use events dated 1 to 31 July 2026 (UTC).
To date | All events up to the end of 31 July 2026.
Sources | Citrus exports from 03 Aug 2026 13:57 UTC. LabConnect inventory report dated 03AUG2026. Site lookup table for site type and activation date.
Weeks | Monday to Sunday. Part weeks at the start or end of the month count only days inside the month.
Enrollment rate | Per site per week = enrollments in the month ÷ 4.43 weeks. Per site per month = enrollments in the month. The 'per active site' rates divide by the number of sites activated by month end. Per month since activation = enrolled to date ÷ months since activation.
Surgery complete | A surgery date is entered on the Post-Surgical Findings form.
Pathology report uploaded | The Post-Surgical Findings form is complete with a report file. The upload date is the form's 'Completed At' time.
Sample registration window | DX1 within 14 days of collection. DX2 within 28 days of collection. DX1 and DX2 must be registered on different days because they ship separately.
Missing pair | One sample of the pair is registered and the other is not. Overdue when the missing sample's window has passed.
Blood sample month view | Counts samples registered at the central lab in the month.
Query status at month end | Closed if closed by month end. Reviewing if the last update before month end moved it to review. Open otherwise.
Days open | Days from query creation to the end of the month, for open and reviewing queries only.